## POA&M
Vulnerability ID | Finding Description | Mitigation Plan | Planned Completion Date | Responsible Party
POA&M-001 | Antivirus signature database is outdated | Update signatures across endpoints via centralized script | 2025-07-05 | System Administrator
POA&M-002 | Password policy does not meet STIG baseline | Apply GPO enforcing complexity, length, and expiration | 2025-07-07 | IAM Engineer
POA&M-003 | Apache server vulnerable to CVE-2022-23943 | Patch to version 2.4.54 and verify through scan | 2025-07-10 | Web Services Team